GOALS:   	Targets for next 6 months

1. Data work – database and summary of data work. DUE DATE:  August 1, 2005

2. Conservation Strategies developed

3. Initiate Communication strategies.  		DUE DATE:  May 25, 2005

Measure and document response.

4. Fund a pilot project (?)

5. Send data back out to the states  			DUE DATE:  September 1, 2005

6. Meeting with the states (at NCTC)		            DATE:  November, 2005

7. Incorporate comments into Conservation Strategy document

DEFINITIONS OF SUCCESS:

- Improved population success

  - Watershed basis

  - Habitat loss basis

  - Percentage watershed improved

  - Community supports effort

    - Federal

    - State

    - NGO

    - political

- Measures of Success

  - MOU between States and Feds

  - Adoption of Resolution of support

  - Coordination for support as partners are already participating

- Refined data (based on gaps)

  - Identified in next 6 months

4.  Build capacity to continue data input

CONSERVATION STRATEGIES

- Analyze ongoing efforts

- Goal Statement – revise based on Steering Committee’s input

- Revise goal statement based on state’s input

- Need a threats document

- Need to include options for action

- What value does the Joint Venture bring to the table?

- Need triage component (Habitat Work Group)

- Current draft of Conservation Strategy:

  - Does not prioritize threats

COMMUNICATION:

Internal:

- Fact Sheet (edit and make changes agreed upon by Steering Committee)

- Cover Letter (revise and recognize NE Technical Committee)

  - Add the following:

    - Resolution of Directors

    - Thank you recognizing state support in data gathering

    - Update on data work

    - Conservation strategy document in process

    - Meeting plans in November

  - Send letter to Directors and copy Chiefs

- Quarterly Reports and updates

- MOU or Action Plan to sign on in November

- Recruit Champion (Director) in Northeast

- Strategic Communications Plan 	DUE DATE:  May 25, 2005

External:

Phase 1

- Media plan

Earned media strategy

- Define audiences:

  - General Public

  - Policy Makers

  - Usergroups / anglers

  - Coalition of NGO’s

    - Environmental groups

    - Fishing groups

    - Outdoor industry

      - LL Bean

      - REI

      - Bass Pro Shops

      - Pategonia

      - Outdoor Writers Association

      - Fisheries Professionals

    - Groups causing some of the problems:
Note: this needs to be defined in Conservation Strategy

      - Home builders

      - DOT’s

      - Road builders

- Change name of EBTJV for public consumption

- Create a standard powerpoint presentation for Steering Committee to allow for

modification to multiple audiences

- Eastern Trout Workshop at Lochhaven

Phase 2:  Did not lay this out

FUNDING:

W-B match

NGO housing

Private funds

- There is no specific funding, but could fit under existing sources:

  - Partners for F & W

  - Fish passage

  - Possible FY 06 add-ons to FWS

Pilot projects

- Align with ongoing projects  (identified by Communications Committee)

- List of funding sources (Hannibal and Leon)

  - USDA (including but not limited to Farm Bill programs)

  - Private sources

NEXT STEPS:

MAY 25:	Outreach and Education Committee submit communications plan to Steering Committee

JUNE 21:   	Steering Committee conference call  2:00 pm EST (CMI will set up)

AUGUST:  	Steering Committee Meeting in August at NCTC (CMI will set up)

NOVEMBER:  Full meeting with states at NCTC (Lila and Hannibal will set up)